## 1 year Plan Updated
| 2024-09-01 |  |  |  | 2024-10-01 |  |  |  | 2024-11-01 |  |  |  | 2024-12-01 |  |  |  | 2025-01-01 |  |  |  | 2025-02-01 |  |  |  | 2025-03-01 |  |  |  | 2025-04-01 |  |  |  | 2025-05-01 |  |  |  | 2025-06-01 |  |  |  | 2025-07-01
| 2024-09-04 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4
Implementation of Stategic Decision
Stakeholder Engagement
Continuous engagement meetings with stakeholders, including the Saida municipality, civil society representatives, Ministry of Environment, Ministry of Industry, and others, to provide updates on progress and plans, ensuring their buy-in and support. | 2024-09-01 2024-09-04: All material is ready and needs to be shared with the civil society
Engage with Waste Generators (implement source sorted collection and treatment depending on the civil society invovlment) | bar: 2025-01-01 W1 to 2025-07-01 W4
Engage with by-Product Collectors (recyclables, RDF…) | bar: 2025-01-01 W1 to 2025-07-01 W4
Governance Structuring and Staff Training
Implementation of safety culture
Coordinate with NTCC regarding the safe on-site behaviors | 2024-09-01 2024-09-04: Follow up with Ahmad on the NTCC
Ensure all workers possess proper PPEs (and ensure fixing the washing machine) | 2024-09-01 2024-09-04: To finalize the list of PPEs by next week
Develop Safety Operationg Procedures | 2024-09-01 2024-09-04: No Update
Train employees on safety measures and following established Safety Operating Procedures | bar: 2024-10-01 W1 to 2024-11-01 W4
Capacity Building & Structuring ( to be developed by Fermendom)
Develop internal training modules for all employees (safety, operation) | bar: 2024-10-01 W1 to 2025-03-01 W4
IBC to share current organigram and existing JDs with Fermendom | bar: 2024-10-01 W1 to 2025-03-01 W4
Design an optimized organigram for IBC governance | bar: 2024-10-01 W1 to 2025-03-01 W4
Write comprehensive job description for the organigram key functions and Staff | bar: 2024-10-01 W1 to 2025-03-01 W4
Design and write processes technical KPIs and quality indicators | bar: 2025-01-01 W1 to 2025-03-01 W4
Implement training programs to enhance staff skills in line with the upgrades | bar: 2025-05-01 W1 to 2025-07-01 W4
MRF: Process Integration & Optimization; SOP Phase 1 and 2 Development
Reception of waste
Reception Area: - Clear sewage lines - Fix potholes in inner roads, road markings and signs to direct traffic - Better lighting inside processing area - Setup road cleaning protocol - Setup daily cleaning protocol for waste processing area - Waste receiving area expansion - Cleaning of road leading to the plant entrance | 2024-09-01 2024-09-04: Chris to follow up with Ahmad ask for a civil engineer to assess the potholes and stuctural assessment of the plant
Prepare the plant for winter | 2024-09-01 2024-09-04: Chris to follow up with Ahmad ask for a civil engineer to assess the potholes and stuctural assessment of the plant
assess water Run-off instrastructure
assess the impact of leachates on the infrastructure of the plant
maintain the run-off water channels | bar: 2024-09-01 2024-09-04 to 2024-10-01 W2
Maintain needed vehicle to keep the run-off water channels clean as Plan B | bar: 2024-09-01 2024-09-04 to 2024-11-01 W1
Fix the floor of the reception area | bar: 2024-09-01 2024-09-04 to 2024-12-01 W4
Gather data regarding the reception of waste
Coordination with NTCC for consistent weight measurement | 2024-09-01 2024-09-04: Task running late no coordination meeting held with NTCC
Monitor the implementation of the new consistent weighting mechanism | bar: 2024-09-01 W4 to 2024-12-01 W4
Implementation of a random load sampling program | bar: 2025-01-01 W1 to 2025-01-01 W4
Existing sorting line
Assess the maintenance procedure and record stops to create stoppage log | 2024-09-01 2024-09-04: On track
Coordination with HWEOL to unify data collection and sharing and stoppage log | 2024-09-01 2024-09-04: On track
Weight the waste being disposed of for landfilling | 2024-09-01 2024-09-04: On track
Determine possible improvments to renew the existing line | 2024-09-01 2024-09-04: Based on the recent updates and due to constraints the current line's capacity will be reduced to the bare minimum to allow the installation of the new line.
Start developing the process to renew the existing line | 2024-09-01 2024-09-04: To renew the existing line after the installation of the new line I am researching new technology implemented in Europe and Canada
Implement the upgrades to the existing line | bar: 2025-05-01 W1 to 2025-07-01 W4
New sorting line
Cooperate with FERMENDOM & PHOENIX for the design of the new sorting line
Finalize the design | 2024-09-01 2024-09-04: On track
Prepare the civil infrastructure of the new processing line | bar: 2024-09-01 W3 to 2024-11-01 W2
Install the new line | bar: 2024-11-01 W3 to 2024-12-01 W4
Testing and commisionning | bar: 2025-01-01 W1 to 2025-01-01 W4
Start of operations with the new processing line | bar: 2025-02-01 W1 to 2025-07-01 W4
Fermentation Process
Conduct a detailed analysis of the current fermentation process, identifying areas for improvement in efficiency and output quality. | bar: 2025-02-01 W1 to 2025-07-01 W4
Rehabilitate composting area | bar: 2025-02-01 W1 to 2025-07-01 W4
Automation of the gas burner in case of gas excess | bar: 2025-02-01 W1 to 2025-07-01 W4
Maintenance Strategy
Capacity development of the existing maintenance team
Assess alternative of outsourcing maintenance with appropriate contracts in place | bar: 2024-09-01 2024-09-04 to 2024-10-01 W4
Setup an equipment maintenance schedule
Wastewater Treatment
Assess current and projected wastewater output from steady state operations | bar: 2025-01-01 W1 to 2025-07-01 W4
Refurbish existing plant and upgrade as needed | bar: 2025-03-01 W1 to 2025-07-01 W4
Legacy waste
Legacy waste
Oversee sampling of legacy waste as per the devised FERMENDOM Plan | bar: 2024-09-01 2024-09-04 to 2025-01-01 W1
Analyse the waste and devise treatment methodology | bar: 2024-09-01 2024-09-04 to 2025-02-01 W3
Acquire the needed machine for the treatment of legacy waste | bar: 2025-02-01 W4 to 2025-07-01 W2
Conduct site civil works and preparations to accommodate waste treatment and products | bar: 2025-02-01 W4 to 2025-07-01 W2
Start treating legacy waste as per the devised treatment methodology | bar: 2024-12-01 W3 to 2025-02-01 W3; 2025-07-01 W3 to 2025-07-01 W4
Establish land reclamation process in cooperation with the municipality and MoE | bar: 2025-02-01 W4 to 2025-07-01 W2